## Summary
Use Case | Description | Results |  |  |  | General Comments
|  | 31/05/2017 | Date2 | Date3 | Date4
UCR2A01_01 | SensorThingsAPI | Pass with comments |  |  |  | As Observations need DOIs no observations are returned
UCR2A02_01 | WebAPI | Pass

## Template
Use Case | From summary |  |  | Results
Description | From summary
Step | Description | Data | Expected Outcome | 31/05/2017 | Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## Test_Instructions
Formal Test Procedure
1 | Each use case has a separate test schedule comprising one or more steps.
2 | Each step has a description, optionally some data to enter, and an expected outcome
3 | Testers should enter data exactly as provided to ensure that tests are repeatable
4 | A test step can have one of four outcomes: (1) Pass (2) Pass with comment (3) Workaround (4) Fail
5 | If the expected outcome matches your experience, the step is marked as 'Pass'.
6 | If the expected outcome does not match your experience, but the system can continue and no error occurs the step is marked as 'Pass' but you should provide a comment on the different outcome. You can also comment if you want to suggest an improvement.
7 | If the test step fails, but you are able to proceed via a workaround (for example by choosing a different option) then flag it as such. This should be used sparingly, and it is better to fail a step than to look for a workaround. Generally, end users should not use this option.
8 | If the step cannot be completed, the system produces an error, or the expected outcome is patently different from what you observe, fail the step.
9 | Always comment a failed step: debugging is much easier if an error message is provided or the system behaviour is described.
10 | Even if the system allows, you should not continue testing beyond a failed step.

## UCR2A01_01
Use Case | UCR2A01_01 |  |  | Results
Description | SensorThingsAPI
Step | Description | Data | Expected Outcome | 31/05/2016 | Comments
1 | Set base URL | http://observationsapi.saeon.nimbusservices.co.za/
2 | Get a list of Things | /SensorThings/Things | Json array of Thing | Pass
3 | Get a Thing | SensorThings/Things(Guid) | Json Thing | Pass
4 | Get a list of Thing Locations | /SensorThings/Things(Guid)/Locations | Json array of Location for Thing | Pass
5 | Get a list of Thing HistoricalLocations | /SensorThings/Things(Guid)/HistoricalLocations | Json array of HistoricalLocation for Thing | Pass
6 | Get a list of Thing Datastreams | /SensorThings/Things(Guid)/Datastreams | Json array of Datastream for Thing | Pass
7 | Get a list of Locations | /SensorThings/Locations | Json array of Location | Pass
8 | Get a Location | /SensorThings/Locations(Guid) | Json Location | Pass
9 | Get a list of Location Things | /SensorThings/Locations(Guid)/Things | Json array of Thing for Location | Pass
10 | Get a list of Location HistoricalLocations | /SensorThings/Locations(Guid)/HistoricalLocations | Json array of HistoricalLocation for Location | Pass
11 | Get a list of HistoricalLocations | /SensorThings/HistoricalLocations | Json array of HistoricalLocation | Pass
12 | Get a HistoricalLocation | /SensorThings/HistoricalLocations(Guid) | Json HistoricalLocation | Pass
13 | Get a list of HistoricalLocation Locations | /SensorThings/HistoricalLocations(Guid)/Locations | Json array of Location for HistoricalLocation | Pass
14 | Get a list of HistoricalLocation Things | /SensorThings/HistoricalLocations(Guid)/Things | Json array of Thing for HistoricalLocation | Pass
15 | Get a list of Datastreams | /SensorThings/Datastreams | Json array of Datastream | Pass
16 | Get a Datastream | /SensorThings/Datastreams(Guid) | Json Datastream | Pass
17 | Get a Datastream Thing | /SensorThings/Datastreams(Guid)/Thing | Json Thing for Datastream | Pass
18 | Get a Datastream Sensor | /SensorThings/Datastreams(Guid)/Sensor | Json Sensor for Datastream | Pass
19 | Get a Datastream ObservedProperty | /SensorThings/Datastreams(Guid)/ObservedProperty | Json ObservedProperty for Datastream | Pass
20 | Get a list of Datastream Observations | /SensorThings/Datastreams(Guid)/Observations | Json array of Observation for Datastream | Pass with comments | As observations need DOIs an empty array is returned
21 | Get a list of Sensors | /SensorThings/Sensors | Json array of Sensor | Pass
22 | Get a Sensor | /SensorThings/Sensors(Guid) | Json Sensor | Pass
23 | Get a list of Sensor Datastreams | /SensorThings/Sensors(Guid)/Datastreams | Json array of Datastream for Sensor | Pass
24 | Get a list of ObservedProperties | /SensorThings/ObservedProperties | Json array of ObservedProperty | Pass
25 | Get an ObservedProperty | /SensorThings/ObservedProperties(Guid) | Json ObservedProperty | Pass
26 | Get a list of ObservedProperty Datastreams | /SensorThings/ObservedProperties(Guid)/Datastreams | Json array of Datastream for ObservedProperty | Pass
27 | Get a list of Observations | /SensorThings/Observations | Json array of Observation | Pass with comments | As observations need DOIs an empty array is returned
28 | Get an Observation | /SensorThings/Observations(Guid) | Json Observation | Pass with comments | As observations need DOIs an empty object is returned
29 | Get an Observation FeatureOfInterest | /SensorThings/Observations(Guid)/FeatureOfInterest | Json FeatureOfInterest for Observation | Pass with comments | As observations need DOIs an empty object is returned
30 | Get an Observation Datastream | /SensorThings/Observations(Guid)/Datastream | Json Datastream for Observation | Pass with comments | As observations need DOIs an empty object is returned
31 | Get a list of FeaturesOfInterest | /SensorThings/FeaturesOfInterest | Json array of FeatureOfInterest | Pass
32 | Get a FeatureOfInterest | /SensorThings/FeaturesOfInterest(Guid) | Json FeatureOfInterest | Pass
33 | Get a list of FeaturesOfInterest Observations | /SensorThings/FeaturesOfInterest(Guid)/Observations | Json array of Observation for FeatureOfInterest | Pass with comments | As observations need DOIs an empty array is returned

## UCR2A02_01
Use Case | UCR2A02_01 |  |  | Results
Description | WebAPI
Step | Description | Data | Expected Outcome | 31/05/2016 | Date 2
1 | Base URL | http://observationsapi.saeon.nimbusservices.co.za/ |  | Pass
2 | Get an access token | Post: https://identity.saeon.nimbusservices.co.za/oauth2/connect/token Header: Content-Type application/x-www-form-urlencoded Body: grant_type:client_credentials client_id:SAEON.Observations.WebAPI client_secret:81g5wyGSC89a scope:SAEON.Observations.WebAPI | Access token | Pass
3 | Do a data query | Post: /DataQuery Header: Authorization:bearer token Content-Type:application/json Body: { "Stations": [ "3471bb22-b79b-40b3-9f75-94ef98ffee00" ], "PhenomenaOfferings": [ "ab394053-3923-4f0c-a4f0-7eb942234794", "f7b3f354-8382-43e5-bd6d-ace413b57d7e", "08561411-96d5-4301-bddd-6584e8db91e0", "e0341b3b-0202-4fba-bc07-8edcdf942ac5", "c77f4b97-1bb3-441b-a9b2-31c3d0fa30f8", "5645231d-55d3-415b-a7a2-9d6bcdd34674", "9ad62278-e26e-438f-bea6-bef0451736ea", "1f9ecde6-eef8-48cd-91d6-649e4ce8e8ba", "9572f605-f11e-4199-b832-440fb8b65240", "e457adf6-5273-4a19-a675-ab30b76832f5", "b129e8bf-bb46-4ab3-88af-3933bc52fd34", "42a2ac0b-560b-4cbf-a48b-bff0091e3f14", "a2ef65a1-384b-448b-b09b-9d487fa18d93", "21afca24-5901-40c5-a7cc-1d8bc8337bbe" ], "StartDate": "1981-06-01T00:00:00+02:00", "EndDate": "1981-08-01T00:00:00+02:00" } | Json results | Pass
4 | Inventory query | Post: /Inventory Header: Authorization:bearer token Content-Type:application/json Body: { "Stations": [ "3471bb22-b79b-40b3-9f75-94ef98ffee00" ], "PhenomenaOfferings": [ "ab394053-3923-4f0c-a4f0-7eb942234794", "f7b3f354-8382-43e5-bd6d-ace413b57d7e", "08561411-96d5-4301-bddd-6584e8db91e0", "e0341b3b-0202-4fba-bc07-8edcdf942ac5", "c77f4b97-1bb3-441b-a9b2-31c3d0fa30f8", "5645231d-55d3-415b-a7a2-9d6bcdd34674", "9ad62278-e26e-438f-bea6-bef0451736ea", "1f9ecde6-eef8-48cd-91d6-649e4ce8e8ba", "9572f605-f11e-4199-b832-440fb8b65240", "e457adf6-5273-4a19-a675-ab30b76832f5", "b129e8bf-bb46-4ab3-88af-3933bc52fd34", "42a2ac0b-560b-4cbf-a48b-bff0091e3f14", "a2ef65a1-384b-448b-b09b-9d487fa18d93", "21afca24-5901-40c5-a7cc-1d8bc8337bbe" ], "StartDate": "1981-06-01T00:00:00+02:00", "EndDate": "1981-08-01T00:00:00+02:00" } | Json results including a list of totals by status with statistics, a list of stations by status with statistics, a list of phenomena by status with statistics, a list of intruments by status with statistics, a list of years by status with statistics, a list of organisations by status with statistics | Pass
5 | Add a user query | Post: /UserQueries Header: Authorization:bearer token Content-Type:application/json Body: { "Name": "Test", "Description": "A test query", "QueryInput": { "Stations": [ "3471bb22-b79b-40b3-9f75-94ef98ffee00" ], "PhenomenaOfferings": [ "ab394053-3923-4f0c-a4f0-7eb942234794", "f7b3f354-8382-43e5-bd6d-ace413b57d7e", "08561411-96d5-4301-bddd-6584e8db91e0", "e0341b3b-0202-4fba-bc07-8edcdf942ac5", "c77f4b97-1bb3-441b-a9b2-31c3d0fa30f8", "5645231d-55d3-415b-a7a2-9d6bcdd34674", "9ad62278-e26e-438f-bea6-bef0451736ea", "1f9ecde6-eef8-48cd-91d6-649e4ce8e8ba", "9572f605-f11e-4199-b832-440fb8b65240", "e457adf6-5273-4a19-a675-ab30b76832f5", "b129e8bf-bb46-4ab3-88af-3933bc52fd34", "42a2ac0b-560b-4cbf-a48b-bff0091e3f14", "a2ef65a1-384b-448b-b09b-9d487fa18d93", "21afca24-5901-40c5-a7cc-1d8bc8337bbe" ], "StartDate": "1981-06-01T00:00:00+02:00", "EndDate": "1981-08-01T00:00:00+02:00" } } | Ok, Location of new user query | Pass
6 | Update a user query | Put: /UserQueries/Guid Header: Authorization:bearer token Content-Type:application/json Body: { "Name": "Test", "Description": "A test query" } | Ok, No content | Pass
7 | Delete a user query | Delete: /UserQueries/Guid Header: Authorization:bearer token Content-Type:application/json | Ok, No content | Pass
8 | Get a list of user queries | Get: /UserQueries Header: Authorization:bearer token Content-Type:application/json | Ok, Json array of user queries for logged in user | Pass
9 | Get a user query | Get: /UserQueries/Guid Header: Authorization:bearer token Content-Type:application/json | Ok, Json user query for logged in user
10 | Add a user download | Post: /UserDownloads Header: Authorization:bearer token Content-Type:application/json Body: { "Name": "Test", "Description": "Test download", "QueryInput": { "Stations": [ "3471bb22-b79b-40b3-9f75-94ef98ffee00" ], "PhenomenaOfferings": [ "ab394053-3923-4f0c-a4f0-7eb942234794", "f7b3f354-8382-43e5-bd6d-ace413b57d7e", "08561411-96d5-4301-bddd-6584e8db91e0", "e0341b3b-0202-4fba-bc07-8edcdf942ac5", "c77f4b97-1bb3-441b-a9b2-31c3d0fa30f8", "5645231d-55d3-415b-a7a2-9d6bcdd34674", "9ad62278-e26e-438f-bea6-bef0451736ea", "1f9ecde6-eef8-48cd-91d6-649e4ce8e8ba", "9572f605-f11e-4199-b832-440fb8b65240", "e457adf6-5273-4a19-a675-ab30b76832f5", "b129e8bf-bb46-4ab3-88af-3933bc52fd34", "42a2ac0b-560b-4cbf-a48b-bff0091e3f14", "a2ef65a1-384b-448b-b09b-9d487fa18d93", "21afca24-5901-40c5-a7cc-1d8bc8337bbe" ], "StartDate": "1981-06-01T00:00:00+02:00", "EndDate": "1981-08-01T00:00:00+02:00" } } | Ok, Location of new user download | Pass
11 | Update a user download | Put: /UserDownloads/Guid Header: Authorization:bearer token Content-Type:application/json Body: { "Name": "Test", "Description": "A test download" } | Ok, No content | Pass
12 | Delete a user dounload | Delete: /UserDownloads/Guid Header: Authorization:bearer token Content-Type:application/json | Ok, No content | Pass
13 | Get a list of user downloads | Get: /UserDownloads Header: Authorization:bearer token Content-Type:application/json | Ok, Json array of user downloads for logged in user | Pass
14 | Get a user download | Get: /UserDownload/Guid Header: Authorization:bearer token Content-Type:application/json | Ok, Json user download for logged in user | Pass