## Summary
Use Case | Description | Results |  |  |  | General Comments
|  | 31/05/2017 | Date2 | Date3 | Date4
UCR2B01_01 | Query Definition Wizard – Login | Pass
UCR2B01_02 | Query Definition Wizard – Save queries | Pass
UCR2B01_03 | Query Definition Wizard – Load queries | Pass
UCR2B01_04 | Query Definition Wizard – Table | Pass with comments |  |  |  | Date filter formats incorrect
UCR2B01_05 | Query Definition Wizard – Cards | Pass
UCR2B01_06 | Query Definition Wizard – Chart | Pass
UCR2B01_07 | Query Definition Wizard – Stations | Pass with comments |  |  |  | Map does not centre properly on load
UCR2B01_08 | Inventory | Pass
UCR2B01_09 | Temporal coverage | Pass
UCR2B01_10 | Spacial coverage | Pass

## Template
Use Case | From summary |  |  | Results
Description | From summary
Step | Description | Data | Expected Outcome | 31/05/2017 | Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## Test_Instructions
Formal Test Procedure
1 | Each use case has a separate test schedule comprising one or more steps.
2 | Each step has a description, optionally some data to enter, and an expected outcome
3 | Testers should enter data exactly as provided to ensure that tests are repeatable
4 | A test step can have one of four outcomes: (1) Pass (2) Pass with comment (3) Workaround (4) Fail
5 | If the expected outcome matches your experience, the step is marked as 'Pass'.
6 | If the expected outcome does not match your experience, but the system can continue and no error occurs the step is marked as 'Pass' but you should provide a comment on the different outcome. You can also comment if you want to suggest an improvement.
7 | If the test step fails, but you are able to proceed via a workaround (for example by choosing a different option) then flag it as such. This should be used sparingly, and it is better to fail a step than to look for a workaround. Generally, end users should not use this option.
8 | If the step cannot be completed, the system produces an error, or the expected outcome is patently different from what you observe, fail the step.
9 | Always comment a failed step: debugging is much easier if an error message is provided or the system behaviour is described.
10 | Even if the system allows, you should not continue testing beyond a failed step.

## UCR2B01_01
Use Case | UCR2B01_01 |  |  | Results
Description | Query Definition Wizard – Login
Step | Description | Data | Expected Outcome | 31/05/2016 | Date 2
1 | Navigate to the Observations Database Query Site | http://observationsquery.saeon.nimbusservices.co.za | Home Page opens with a login menu | Pass
2 | Click on the ‘Account’ dropdown menu and click on 'Login' and enter credentials. | Username: guest@saeon.ac.za Password: S@E0NGue$t | Successful login with the Query Site home page appearing | Pass
3 | Ensure that the menu has ‘Home’, ‘Query’, ‘About’, ‘Contact’, ‘Account’ items |  | The menu has ‘Home’, ‘Query’, ‘About’, ‘Contact’, ‘Account’ items | Pass
4 | Click on the ‘Account’ dropdown menu and click on 'Logout' |  | Account menu has ‘Login’ and ‘Register’ items | Pass
5 | Click on the ‘Account’ dropdown menu and click on 'Login' and enter credentials. | Username: admin@saeon.ac.za Password: S@E0N@dm1n | Successful login with the Query Site home page appearing | Pass
6 | Ensure that the menu has ‘Home’, ‘Query’, ‘Admin’, ‘About’, ‘Contact’, ‘Account’ items |  | The menu has ‘Home’, ‘Query’, ‘Admin’, ‘About’, ‘Contact’, ‘Account’ items | Pass
7 | Click on the ‘Account’ dropdown menu and click on 'Logout' |  | Account menu has ‘Login’ and ‘Register’ items | Pass

## UCR2B01_02
Use Case | UCR2B01_02 |  |  | Results
Description | Query Definition Wizard – Save queries
Step | Description | Data | Expected Outcome | 31/05/2016 | Date 2
1 | Navigate to the Observations Database Query Site | http://observationsquery.saeon.nimbusservices.co.za | Home Page opens with a login menu | Pass
2 | Click on the ‘Account’ dropdown menu and click on 'Login' and enter credentials. | Username: guest@saeon.ac.za Password: S@E0NGue$t | Successful login with the Query Site home page appearing | Pass
3 | Click on the ‘Query’ menu item |  | Query form opens | Pass
4 | Expand the ‘SAEON’ node in the ‘Where’ tab |  | The ‘SAEON’ node expands | Pass
5 | Tick the ‘Witklip’ site |  | The ‘Selected’ list includes ‘Witklip’ | Pass
6 | Click on the ‘What’ tab |  | The ‘What’ tab opens with a tree of Phenomena | Pass
7 | Tick the ‘Humidity’ node |  | The ‘Selected’ list includes as set of ‘Humidity’ offerings | Pass
8 | Tick the ‘Temperature’ node |  | The ‘Selected’ list includes as set of ‘Temperature’ offerings | Pass
9 | Click on the ‘When’ tab |  | The ‘When’ tab opens | Pass
10 | Select the Start Date and End Date as ‘01 Jun 1981’ and ‘31 Aug 1981’ | Start Date: 01 Jun 1981 End Date: 31 Aug 1981 | The ‘Start Date’ and ‘End Date’ have values ‘01 Jun 1981’ and ‘31 Aug 1981’ | Pass
11 | Click on the ‘Save Query’ button and fill in the relevant fields in the popup and click on the ‘Save’ button | Name: Test Description: Test | The 'Save Query' popup dialog closes | Pass
12 | Click on the ‘Account’ dropdown menu and click on 'My Queries' |  | The ‘User Queries’ form opens | Pass
13 | Verify that the ‘Test’ user query is in the list of queries displayed |  | The ‘Test’ user query is in the list of queries displayed | Pass
14 | Click on the ‘Edit’ link in the row with ‘Name’ ‘Test’ | Name: Test | The ‘User Query’ form opens with ‘Test’ | Pass
15 | Change the ‘Description’ to ‘Test description’ and click on the ‘Save’ button | Description: Test description | The 'Test' user query has a Description of 'Test Description | Pass
16 | Click on the 'Delete' link |  |  | Pass
17 | Verify the 'Test' user query is not in the list of queries displayed |  | The 'Test' user query is not in the list of queries displayed | Pass

## UCR2B01_03
Use Case | UCR2B01_03 |  |  | Results
Description | Query Definition Wizard – Load queries
Step | Description | Data | Expected Outcome | 31/05/2016 | Date 2
1 | Navigate to the Observations Database Query Site | http://observationsquery.saeon.nimbusservices.co.za | Home Page opens with a login menu | Pass
2 | Click on the ‘Account’ dropdown menu and click on 'Login' and enter credentials. | Username: guest@saeon.ac.za Password: S@E0NGue$t | Successful login with the Query Site home page appearing | Pass
3 | Click on the ‘Query’ menu item |  | Query form opens | Pass
4 | Click on the 'Load Query' button |  | The 'Load Query' dialog opens | Pass
5 | In the 'Name' dropdown select 'Test' and click on the 'Load' button | Name: Test | The query is loaded and the 'Where' tab has 'Witklip' selected, the 'What' tab has 'Humidity' and 'Temperature' selected and the 'When' tab has 'Start Date' with value '01 Jun 1982' and 'End Date' has '31 Aug 1981' | Pass

## UCR2B01_04
Use Case | UCR2B01_04 |  |  | Results
Description | Query Definition Wizard – Table
Step | Description | Data | Expected Outcome | 31/05/2016 | Comments
1 | Navigate to the Observations Database Query Site | http://observationsquery.saeon.nimbusservices.co.za | Home Page opens with a login menu | Pass
2 | Click on the ‘Account’ dropdown menu and click on 'Login' and enter credentials. | Username: guest@saeon.ac.za Password: S@E0NGue$t | Successful login with the Query Site home page appearing | Pass
3 | Click on the ‘Query’ menu item |  | Query form opens | Pass
4 | Click on the 'Load Query' button |  | The 'Load Query' dialog opens | Pass
5 | In the 'Name' dropdown select 'Test' and click on the 'Load' button | Name: Test | The query is loaded and the 'Where' tab has 'Witklip' selected, the 'What' tab has 'Humidity' and 'Temperature' selected and the 'When' tab has 'Start Date' with value '01 Jun 1982' and 'End Date' has '31 Aug 1981' | Pass
6 | Click on the 'Search' button |  | Progress indicator is displayed until data is loaded | Pass
7 | Click on the 'Table' tab |  | Table tab is selected with grid of data | Pass
8 | Click on the 'Date' column header |  | Data should be displayed in descending order | Pass
9 | Click on the 'Date' column header |  | Data should be displayed in ascending order | Pass
10 | Click on the 'Filter' button on the 'Date' header | Filter: Date | Popup with filter options is displayed | Pass
11 | Hover on 'Date filters' and click on 'Greater than' |  | Custom Filter popup is displayed | Pass
12 | Select the date '22 Jul 1981' and click on the 'OK' button | Date: 22 Jul 1981 | Only dates from 22 Jul 1981 are displayed | Pass with comment | Formats of dates in filters is incorrect. Will investiagte
13 | Click on the 'Filter' button on the 'Date' header |  | Popup with filter options is displayed | Pass
14 | Click on 'Clear filters' |  | All dates are shown | Pass
15 | At the bottom of the grid click on the '>' button |  | The 2nd page of data is shown | Pass
16 | At the bottom of the grid click on the '<' button |  | The 1st page of data is shown | Pass
17 | At the bottom of the grid click on the '>¦' button |  | The last page of data is shown | Pass
18 | At the bottom of the grid click on the '¦<' button |  | The first page of data is shown | Pass

## UCR2B01_05
Use Case | UCR2B01_05 |  |  | Results
Description | Query Definition Wizard – Cards
Step | Description | Data | Expected Outcome | 31/05/2016 | Comments
1 | Navigate to the Observations Database Query Site | http://observationsquery.saeon.nimbusservices.co.za | Home Page opens with a login menu | Pass
2 | Click on the ‘Account’ dropdown menu and click on 'Login' and enter credentials. | Username: guest@saeon.ac.za Password: S@E0NGue$t | Successful login with the Query Site home page appearing | Pass
3 | Click on the ‘Query’ menu item |  | Query form opens | Pass
4 | Click on the 'Load Query' button |  | The 'Load Query' dialog opens | Pass
5 | In the 'Name' dropdown select 'Test' and click on the 'Load' button | Name: Test | The query is loaded and the 'Where' tab has 'Witklip' selected, the 'What' tab has 'Humidity' and 'Temperature' selected and the 'When' tab has 'Start Date' with value '01 Jun 1982' and 'End Date' has '31 Aug 1981' | Pass
6 | Click on the 'Search' button |  | Progress indicator is displayed until data is loaded | Pass
7 | Click on the 'Cards' tab |  | Cards tab is selected with a list of cards for each station | Pass

## UCR2B01_06
Use Case | UCR2B01_06 |  |  | Results
Description | Query Definition Wizard – Chart
Step | Description | Data | Expected Outcome | 31/05/2016 | Comments
1 | Navigate to the Observations Database Query Site | http://observationsquery.saeon.nimbusservices.co.za | Home Page opens with a login menu | Pass
2 | Click on the ‘Account’ dropdown menu and click on 'Login' and enter credentials. | Username: guest@saeon.ac.za Password: S@E0NGue$t | Successful login with the Query Site home page appearing | Pass
3 | Click on the ‘Query’ menu item |  | Query form opens | Pass
4 | Click on the 'Load Query' button |  | The 'Load Query' dialog opens | Pass
5 | In the 'Name' dropdown select 'Test' and click on the 'Load' button | Name: Test | The query is loaded and the 'Where' tab has 'Witklip' selected, the 'What' tab has 'Humidity' and 'Temperature' selected and the 'When' tab has 'Start Date' with value '01 Jun 1982' and 'End Date' has '31 Aug 1981' | Pass
6 | Click on the 'Search' button |  | Progress indicator is displayed until data is loaded | Pass
7 | Click on the 'Chart' tab |  | Chart tab is selected with a chart with the selected phenomena’s observations | Pass
8 | Scroll up on the mouse wheel to zoom in | Mouse wheel scroll | Chart should zoom in | Pass
9 | Click on the ‘Zoom in’ button |  | Chart should zoom in | Pass
10 | Click on the ‘Zoom out’ button |  | Chart should zoom out | Pass
11 | Drag the X axis scrollbar to the right |  | Chart should pan to the right | Pass
12 | Drag the X axis scrollbar to the left |  | Chart should pan to the left | Pass
13 | Click on the right hand circle on the X axis scrollbar and drag left |  | Chart should zoom in on X axis only | Pass
14 | Click on the right hand circle on the X axis scrollbar and drag right |  | Chart should zoom out on X axis only | Pass
15 | Click on the left hand circle on the X axis scrollbar and drag right |  | Chart should zoom in on X axis only | Pass
16 | Click on the left hand circle on the X axis scrollbar and drag left |  | Chart should zoom out on X axis only | Pass
17 | Drag the Y axis scrollbar to the up |  | Chart should pan to the up | Pass
18 | Drag the Y axis scrollbar to the down |  | Chart should pan to the down | Pass
19 | Click on the top circle on the Y axis scrollbar and drag down |  | Chart should zoom in on Y axis only | Pass
20 | Click on the top hand circle on the Y axis scrollbar and drag up |  | Chart should zoom out on Y axis only | Pass
21 | Click on the bottom hand circle on the Y axis scrollbar and drag up |  | Chart should zoom in on Y axis only | Pass
22 | Click on the bottom hand circle on the Y axis scrollbar and drag down |  | Chart should zoom out on Y axis only | Pass
23 | Click on the ‘Pan’ button and then click and drag on the chart |  | Chart should pan with the mouse | Pass
24 | Click on the ‘Reset’ button |  | Chart should return to its original size | Pass

## UCR2B01_07
Use Case | UCR2B01_07 |  |  | Results
Description | Query Definition Wizard – Stations
Step | Description | Data | Expected Outcome | 31/05/2016 | Comments
1 | Navigate to the Observations Database Query Site | http://observationsquery.saeon.nimbusservices.co.za | Home Page opens with a login menu | Pass
2 | Click on the ‘Account’ dropdown menu and click on 'Login' and enter credentials. | Username: guest@saeon.ac.za Password: S@E0NGue$t | Successful login with the Query Site home page appearing | Pass
3 | Click on the ‘Query’ menu item |  | Query form opens | Pass
4 | Expand the ‘SAEON’ node in the ‘Where’ tab |  | The ‘SAEON’ node expands | Pass
5 | Tick the ‘Witklip’ site |  | The ‘Selected’ list includes ‘Witklip’ | Pass
6 | Click on the 'Stations' tab |  | Map in Stations tab has the selected stations in green, unselected in red | Pass
7 | Click on the ‘Where’ tab, expand the ‘SAEON’ node, untick the ‘Witkip’ site |  | Map in Stations tab has all stations in red | Pass

## UCR2B01_08
Use Case | UCR2B01_08 |  |  | Results
Description | Inventory
Step | Description | Data | Expected Outcome | 31/05/2016 | Comments
1 | Navigate to the Observations Database Query Site | http://observationsquery.saeon.nimbusservices.co.za | Home Page opens with a login menu | Pass
2 | Click on the ‘Account’ dropdown menu and click on 'Login' and enter credentials. | Username: admin@saeon.ac.za Password: S@E0N@dm1n | Successful login with the Query Site home page appearing | Pass
3 | Click on the ‘Admin’ dropdown menu and click on ‘Inventory’ |  | Inventory form opens and expands Totals to display a grid with statistics for each of the statuses | Pass
4 | Click on the ‘+’ next to ‘Stations’ |  | Stations expands to display a grid with statistics for station and status | Pass
5 | Click on the ‘+’ next to ‘Phenomena’ |  | Phenomena expands to display a grid with statistics for each phenomenon and status | Pass
6 | Click on the ‘+’ next to ‘Instruments’ |  | Instruments expands to display a grid with statistics for each instrument and status | Pass
7 | Click on the ‘+’ next to ‘Years’ |  | Years expands to display a grid with statistics for each year and status | Pass
8 | Click on the ‘+’ next to ‘Organisations’ |  | Organisations expands to display a grid with statistics for each organisation and status | Pass

## UCR2B01_09
Use Case | UCR2B01_09 |  |  | Results
Description | Temporal coverage
Step | Description | Data | Expected Outcome | 31/05/2016 | Comments
1 | Navigate to the Observations Database Query Site | http://observationsquery.saeon.nimbusservices.co.za | Home Page opens with a login menu | Pass
2 | Click on the ‘Account’ dropdown menu and click on 'Login' and enter credentials. | Username: admin@saeon.ac.za Password: S@E0N@dm1n | Successful login with the Query Site home page appearing | Pass
3 | Click on the ‘Admin’ dropdown menu and click on ‘Temporal Coverage’ |  | Temporal coverage form opens with tabs for When, What, Where and Chart | Pass
4 | Expand the ‘SAEON’ node in the ‘Where’ tab |  | The ‘SAEON’ node expands | Pass
5 | Tick the ‘Witklip’ site |  | The ‘Selected’ list includes ‘Witklip’ | Pass
6 | Click on the ‘What’ tab |  | The ‘What’ tab opens with a tree of Phenomena | Pass
7 | Tick the ‘Humidity’ node |  | The ‘Selected’ list includes as set of ‘Humidity’ offerings | Pass
8 | Tick the ‘Temperature’ node |  | The ‘Selected’ list includes as set of ‘Temperature’ offerings | Pass
9 | Click on the ‘When’ tab |  | The ‘When’ tab opens | Pass
10 | Select the Start Date and End Date as ‘Jan 1987’ and ‘Feb 1987’ | Start Date: Jan 1987 End Date: Feb 1987 | The ‘Start Date’ and ‘End Date’ have values ‘Jan 1987’ and ‘Feb 1987’ | Pass
11 | Click on the ‘Search’ button |  | After progress indicator close the ‘Chart’ tab has a chart for the selected Stations and Phenomena | Pass
12 | Click on the ‘Chart’ tab |  | The ‘Chart’ tab opens | Pass
13 | Verify that there are dates with status ‘Verified’, ‘Being Verified’,’Unverified’ and ‘No Status’ |  | There are dates with status ‘Verified’, ‘Being Verified’,’Unverified’ and ‘No Status’ | Pass

## UCR2B01_10
Use Case | UCR2B01_10 |  |  | Results
Description | Spacial coverage
Step | Description | Data | Expected Outcome | 31/05/2016 | Comments
1 | Navigate to the Observations Database Query Site | http://observationsquery.saeon.nimbusservices.co.za | Home Page opens with a login menu | Pass
2 | Click on the ‘Account’ dropdown menu and click on 'Login' and enter credentials. | Username: admin@saeon.ac.za Password: S@E0N@dm1n | Successful login with the Query Site home page appearing | Pass
3 | Click on the ‘Admin’ dropdown menu and click on ‘Spacial Coverage’ |  | Spacial coverage form opens with tabs for When, What, Where and Map | Pass
4 | Expand the ‘SAEON’ node in the ‘Where’ tab |  | The ‘SAEON’ node expands | Pass
5 | Tick the ‘Witklip’ site |  | The ‘Selected’ list includes ‘Witklip’ | Pass
6 | Click on the ‘What’ tab |  | The ‘What’ tab opens with a tree of Phenomena | Pass
7 | Tick the ‘Humidity’ node |  | The ‘Selected’ list includes as set of ‘Humidity’ offerings | Pass
8 | Tick the ‘Temperature’ node |  | The ‘Selected’ list includes as set of ‘Temperature’ offerings | Pass
9 | Click on the ‘When’ tab |  | The ‘When’ tab opens | Pass
10 | Select the Start Date and End Date as ‘Jan 1987’ and ‘Feb 1987’ | Start Date: Jan 1987 End Date: Feb 1987 | The ‘Start Date’ and ‘End Date’ have values ‘Jan 1987’ and ‘Feb 1987’ | Pass
11 | Click on the ‘Search’ button |  | After progress indicator close the ‘Map’ tab has a map for the selected Stations | Pass
12 | Click on the ‘Map’ tab |  | The ‘Map’ tab opens | Pass
13 | Verify that there are stations with status ‘Verified’, ‘Being Verified’,’Unverified’ and ‘No Status’ |  | There are station with status ‘Verified’, ‘Being Verified’,’Unverified’ and ‘No Status’ | Pass